## Risk Register
Risk ID | Risk Scenario | Assets / Business Area | Likelihood (1-5) | Impact (1-5) | Inherent Score | Inherent Level | Recommended Controls / Treatment | NIST CSF 2.0 Mapping | Suggested Owner Role | Target Date | Illustrative Residual Risk | Next Action
R01 | Phishing email leads to credential theft or malware execution | Email users and endpoints | 4 | 5 |  |  | Email filtering; phishing-awareness training; MFA; report-phishing process | Protect / Detect | IT Security Lead | 30 days | Medium | Enable MFA and run a phishing-awareness session
R02 | Unpatched operating system or application is exploited | Servers and workstations | 4 | 4 |  |  | Asset inventory; risk-based patching; vulnerability scanning | Identify / Protect | IT Operations | 30 days | Medium | Prioritize critical and internet-facing assets
R03 | Ransomware spreads laterally across the network | Endpoints, file shares, servers | 3 | 5 |  |  | Network segmentation; endpoint detection; least privilege; restrict admin tools | Protect / Detect | Network Administrator | 60 days | Medium | Separate user devices from critical servers
R04 | Backups are encrypted, deleted, or unavailable during recovery | Backup repositories and business data | 3 | 5 |  |  | Offline or immutable backups; separate backup credentials; routine restore tests | Protect / Recover | Backup Administrator | 30 days | Low–Medium | Perform and document a sample restore test
R05 | Excessive privileges enable broad system compromise | Identity and access management | 3 | 4 |  |  | Least privilege; privileged account separation; periodic access reviews; MFA | Govern / Protect | IAM Administrator | 45 days | Medium | Review administrator and service accounts
R06 | Suspicious activity is not detected quickly | Logs, endpoints, identity systems | 3 | 4 |  |  | Centralized logging; alerting; time synchronization; incident triage procedure | Detect | Security Analyst | 45 days | Medium | Collect endpoint, identity, and server logs
R07 | Incident response roles and communications are unclear | Business operations and response team | 3 | 4 |  |  | Written incident response plan; contact list; tabletop exercise | Govern / Respond | Incident Response Coordinator | 30 days | Medium | Assign incident commander and escalation contacts
R08 | Sensitive data is exposed during or after an incident | Customer and business data | 2 | 5 |  |  | Data classification; encryption; access controls; legal/privacy escalation path | Identify / Protect / Respond | Data Protection Owner | 60 days | Medium | Identify sensitive data stores and owners
R09 | Third-party remote access is abused | Vendor access and remote administration | 3 | 4 |  |  | MFA; time-limited access; vendor reviews; approved remote-access gateway | Govern / Protect | Vendor Risk Owner | 60 days | Medium | Remove dormant vendor accounts
R10 | Recovery is delayed because restoration priorities are unknown | Critical business services | 3 | 4 |  |  | Business impact analysis; recovery priorities; tested recovery-time objectives | Recover / Govern | Business Continuity Lead | 60 days | Medium | List critical services and recovery order

## Scoring Guide
Field | Definition
Likelihood (1-5) | 1 Rare; 2 Unlikely; 3 Possible; 4 Likely; 5 Almost certain. Tailor ratings to evidence in a real assessment.
Impact (1-5) | 1 Insignificant; 2 Minor; 3 Moderate; 4 Major; 5 Severe. Consider service outage, data loss, financial and legal effects.
Inherent score | Likelihood × Impact, before additional proposed treatment actions.
Level thresholds | 1–5 Low; 6–14 Medium; 15–25 High. Project-defined thresholds, not universal NIST ratings.
Residual risk | Illustrative qualitative estimate after proposed controls. Validate after implementation and testing.
NIST CSF mapping | High-level mapping to Govern, Identify, Protect, Detect, Respond, Recover; not a formal control-by-control compliance mapping.
Scope note | Hypothetical example only. Validate assets, assumptions, scores, owners and dates with the actual organization.